## Sheet1
Software bug report
Project name: | Banking App Prototype
Bug ID | Title/Summary | Issue type | Classification | Environment | Step-by-step | Expected result | Actual result | Frequency | Status | Severity | Notes/Comments | Resolution
[Unique bug name] | [Give a short and clear description of the issue] | Issue type | Classification | [Describe the exact conditions in which the bug appeared. E.g., OS, OS version, app type, app version, etc.] | [List the exact steps you took before the issue manifested] | [Describe what was supposed to happen] | [Describe what actually happened] | Frequency | To do | Severity | [Additional notes or comments regarding the issue] | [Describe how the issue was resolved for future reference]
BUG-001 | Incorrect initial balance set for new accounts | Bug | Syntax | OS: Windows 11 Pro; IDE: IntelliJ IDEA Community Edition 2024.1.1; SDK: Eclipse Temurin 19.0.2 | 1. Run application 2. Login with cheat login 3. Choose option 1 (Add account) 4. Select account type 1 (SBA) 5. Enter name (just hit enter) 6. Check balance (option 5) 7. Repeat for type 2 Community and 3 Client | Initial balance for all newly created accounts should be 0.0. | On account creation of each type the starting blances were not 0 as expected. SBA is £1, Community £2, Client £3 | Always | Done | Critical | Caused by passing accountType int to BankAccount constructors balance parameter in Main.java. Affects MainTest.testDeposit & MainTest.testCheckBalance failures. I rated critical due to the fact there is a risk of major financial loss to the business as the cumalitive affect of adding even £1 could be massive if say 1 million users withdrew the 'free' £1. | Refactored BankAccount and subclasses to use BigDecimal for balance. Modified AccountService.createAccount to initialise balance with BigDecimal.ZERO instead of passing the account type integer. This ensures all new accounts start with zero balance, resolving the incorrect initial balance issue.
BUG-002 | Small Business Account withdrawal does not update balance | Bug | Logic | OS: Windows 11 Pro; IDE: IntelliJ IDEA Community Edition 2024.1.1; SDK: Eclipse Temurin 19.0.2 | 1. Create SBA (Account 1). 2. Deposit £100 into Account 3. Verify balance is £101 (due to BUG-001) 4. Withdraw £50 from Account 5. Check balance of Account again | Succesful withdrawal should print to console and balance should decrease by £50 to £51. | On withdrawing from an SBA withdrawal prints "Withdrawal successful!" but the balance remains £101. | Always | Done | Major | The withdraw method in SmallBusinessAccount calls an empty private void setBalance(double d) {} method, so the balance field is never updated. Breaks core functionality (REQ-007). | I removed the empty setBalance method from the original SBA class and implemented withdraw logic in OverdraftManagement class, ensuring super.setBalance is called correctly to update the balance field after withdrawal. The withdraw method now correctly recognises standard withdrawals and overdraft usage,
BUG-003 | Overdraft facility not applied during withdrawals | Bug | Logic | OS: Windows 11 Pro; IDE: IntelliJ IDEA Community Edition 2024.1.1; SDK: Eclipse Temurin 19.0.2 | 1. Create an account of any type 2. Attempt to withdraw or transfer an amount exceeding balance but within the overdraft limit 3. Repeat for other account types | Withdrawal should be successful as there's an overdraft on each account. Balance should become £0 or negative and overdraft use should be tracked. | Withdrawal and transfers should be possible within each account types overdraft limit but it is not possible to use the overdraft limit on any account. | Always | Done | Major | Fails REQ-005. Community/Client accounts need withdraw overridden to handle overdraft. SBA withdraw needs fixing (BUG-002) and potentially refinement of overdraft logic. | Implemented overdraft logic within the OverdraftManagement.withdraw method. This method checks available funds balance + remaining overdraft before allowing withdrawal. Overdraft limits are specific to each account type.
BUG-004 | System allows creation of multiple accounts of the same type | Bug | Logic | OS: Windows 11 Pro; IDE: IntelliJ IDEA Community Edition 2024.1.1; SDK: Eclipse Temurin 19.0.2 | 1. Create an SBA account 2. Attempt to create another SBA account 3. Repeat with other account types | For duplicate account creation to be prevented. | System successfully creates the second SBA account without any warning or error. | Always | Done | Critical | Violates REQ-002. Main.java account creation logic lacks a check against existing accounts in the accounts list for the type being added. | Added AccountService.accountTypeExistsForUser method. Modified Menu.createBankAccount to call this method and prevent the ability to create duplicate account types. The severity is rated critical due to the financial exploit potential. The repetitive nature of the exploit makes it highly vulnerable to automation or coordinated efforts, potentially leading to significant financial losses for the business.
BUG-005 | User not prompted to create an account if none exist upon login | Missing feature | Logic | OS: Windows 11 Pro; IDE: IntelliJ IDEA Community Edition 2024.1.1; SDK: Eclipse Temurin 19.0.2 | 1. Ensure no user accounts exist when rerunning 2. Login successfully | To be prompted to create a bank account with the types available after logging in with a newly made account. | System proceeds directly to the main menu options without prompting for account creation. | Always | Done | Minor | Fails REQ-003. Requires adding a check if (atm.accounts.isEmpty()) after successful login in Main.java and implementing the prompt logic. | Implemented Menu.checkAndPromptForBankAccountCreation method to be called after login in Menu.runMainMenu. This method checks if accountService.getAccountsForUser checks if the user currenlt has any accounts and if not then it prompts the account creation.
BUG-006 | Two signatory functionality missing | Missing feature | Logic | OS: Windows 11 Pro; IDE: IntelliJ IDEA Community Edition 2024.1.1; SDK: Eclipse Temurin 19.0.2 | N/A (Functionality cannot be invoked as it doesn't exist). Attempting to conceptualize how it should work reveals no implementation | Accounts requiring two signatories should enforce this rule for specific actions such as withdrawals, transfers. | The TwoSignatoriesRestriction method in BankAccount returns false and is never called. No logic exists anywhere to implement or check for this requirement. | Always | Done | Critical | Fails REQ-004. This is a significant feature gap requiring design (how are signatories stored/checked?) and implementation across relevant methods. | Implemented requiresSignatoryAuth() method for the Community account as per the requirements set out by the PO and BA. Added checks in Menu.withdraw, Menu.transfer, and Menu.closeBankAccount to prevent actions on signatory required accounts.
BUG-007 | BankAccount.transfer method always returns false | Bug | Logic | OS: Windows 11 Pro; IDE: IntelliJ IDEA Community Edition 2024.1.1; SDK: Eclipse Temurin 19.0.2 | 1. Create two accounts (Acc1, Acc2). 2. Deposit funds into Acc1. 3. Perform a transfer from Acc1 to Acc2 (ensure sufficient funds). 4. Observe the console output (shows success) and ideally check the return value programmatically (requires test modification or debugging). | The transfer method should return true when the transfer is successful. | The method returns false even when the transfer completes successfully and balances are updated correctly. The console message correctly indicates success, but the method's return value is wrong. | Always | Done | Minor | The return false; statement at the end of the BankAccount.transfer method is incorrect. It should return true after successfully updating balances. Doesn't break the transfer itself but provides incorrect programmatic feedback. Affects REQ-007 slightly (function exists but flawed). | Refactored BankAccount.transferTo method. It now correctly calls the withdraw method which returns true/false. The transferTo method itself now returns true only if the withdrawal was successful, ensuring correct feedback.
BUG-008 | REQ001 Manage account functionality is limited | Suggestion | UI/Usability | OS: Windows 11 Pro; IDE: IntelliJ IDEA Community Edition 2024.1.1; SDK: Eclipse Temurin 19.0.2 | 1. Login 2. Review menu options to see if account managment is implemeted | To be able to manage an account after creation, this should include basic applications such as ability to update username and password and account deletion. | Only options for Add, Deposit, Withdraw, Transfer, Check Balance, Exit are provided. No option to list all accounts or perform account management tasks. | Always | Done | Minor | Current code base only covers basic transactions. Action: Clarify the requirment with PO/BA. If more features are required, add to code base. | Added "View My Bank Accounts" (option 6) and "Account Settings" (option 7, leading to a submenu with Change Username/Password, Close Account) to Menu.displayMainMenu and implemented corresponding methods (viewMyAccounts, runManageAccountMenu) to provide broader account management capabilities, addressing the ambuiguities of REQ-001.